## todo list(day)
Date | IsUrgent | User Name | Account Name | Name | Description | ImportanceLevel | TriggeredBy | DifficultyLevel | 크기(규모)에 따른 분류 | Field(분야) | 분류 - Category? | IsBottleNeck | HasBottleNeckOnStart only for this task | BottleNeckOnStart | BottleNeckOnGing | CanIncreaseWorkEfficiency | ?(아직 이름을 못정함) | Status
2021-07-01 | F | root lim | gwldlqslek | create instagram accounts | K-가요, youuunoiee, 앙드레림 | Super High (High + Main Project/Field) |  | Low (JustTimeConsuming) | Small | Project Manage | SNS | F | F |  | 인스타그램의 정책 때문에 만들지 못하고 있음 | F | BuildUp | StoppedTemporarily
2021-07-01 | F | root lim | ttkmw | workasm gui | management page | High |  | High | Small | Develop | Front | F | F |  | emotion indexing | F | Target | OnGoing
2021-06-01 | F | root lim | gwldlqslek | beyond eyeisght gmail 및 insta 계정 만들기 | 제곧내 | High |  |  | Task | Project Manage | SNS | F | T | contact@beyondeyesight.group 계정 알아보기 | Current Work | F | BuildUp | Finished
2021-07-01 | F |  | gwldlqslek | 유튜브 계정 만들기 | Beyond Eyesight Production | High |  | Low (JustTimeConsuming) | Small | Project Manage | SNS | F | F | https://support.google.com/a/answer/9000768 | Current Work | F | BuildUp | Finished
2021-06-01 | F | root lim | gwldlqslek | contact@beyondeyesight.grou+[@[Accoun+[@이름] | 제곧내 | High |  |  | Task | Project Manage | SNS | T | N |  | Current Work | F | BuildUp | Finished
2021-07-01 | F | root lim | ttkmw | 인스타그램 api 리서치 | 제곧내 | High |  | Low | Small | Research | Backend | F | F |  | Current Work | F | BuildUp | Not Started
2021-07-01 | F | root lim | Shawn Killan | 목소리 변조 리서치 | 제곧내 | High |  | Low | Small | Research | Music Engineer | F | F |  | Current Work | F | BuildUp | Not Started
2021-07-01 | F | root lim | ttkmw | AI mimic vocal 리서치 | 제곧내 | High |  | High | Small | Research | AI Engineer | F | F |  | Current Work | F | CoreBuildUp | Not Started
2021-07-01 | F | root lim | ttkmw | Time Traker 모바일 앱 | 제곧내 | High |  | High | Big | Develop | Mobile Develop | F | F |  | Current Work | F | Target | Not Started
2021-07-01 | F | root lim | ttkmw | beyondeyesight/area | 제곧내 | High |  | Too High | Big | Develop | Backend Develop | F | F |  | Current Work | F | Target | Not Started
2021-07-01 | F | root lim | ttkmw | beyondeyesight/rank | 제곧내 | High |  | High | Big | Develop | Backend Develop | F | F |  | Current Work | F | Target | Not Started
2021-07-01 | F | root lim | ttkmw | beyondeyesight/auction | 제곧내 | High |  | High | Big | Develop | Backend Develop | F | F |  | Current Work | F | Target | Not Started
2021-07-01 | F | root lim | ttkmw | beyondeyesight/collaboration | 제곧내 | High |  | High | Big | Develop | Backend Develop | F | F |  | Current Work | F | Target | Not Started
2021-07-01 | F | root lim | ttkmw | beyondeyesight/HumanRelationship | 제곧내 | High |  | High | Big | Develop | Backend Develop | F | F |  | Current Work | F | Target | Not Started
2021-07-01 | F | root lim | ttkmw | beyondeyesight/Payment | 제곧내 | High |  | High | Big | Develop | Backend Develop | F | F |  | Current Work | F | Target | Not Started
2021-06-03 | F | root lim | ttkmw | beyondeyesight/Battle | 제곧내 | High |  | High | Project | Develop | Backend Develop | F | F |  |  | F | Target | Finished
2021-06-03 | F | root lim | gwldlqslek | make out todos | 제곧내 | High |  | Low | Chore | Documentation | Architect | F | F |  |  | T | Target | Finished
2021-07-01 | F | root lim | Shawn Killan | 동영상 찍고, 편집 | 제곧내 | High |  | Middle | Small | Video Engineer | Video Edit | T | F |  | Current Work | F | Target | Not Started
2021-07-01 | F | root lim | AlGEDBoy | 체인지업 슬랙 들어가기 | 제곧내 | Middle |  | Low | Small | ETC(DocumentTation?) | Customer | F | F |  |  | F | BuildUp | Finished
2021-07-01 | F | root lim | ttkmw | dynamic side bar | 현재 side bar에서 scroll은 되지만, 위치가 고정됨. Dynamic하게 만들면 좋을듯 | Middle | 대사용자 배포 | High | Middle | Develop | Frontend Develop | F | F | null | Current Work | F | Target | Not Started

## Time Tracker(Time Table)
Start Date | Start Time | End Date | End Time | User Name | Character Name | Expected Work | Expected Period | ExpectedTimeCategory | Actual Work | Acutal Period | ActualTimeCategory | ContextChange | TriggerdBy | SuccessingWorkOn(Event) | Self Feedback Number | OrdinaryTask | ShouldBeRespected(ShowedPerformance/WowPoint) | Self Feedback Text | BottleNeck Logs(Task 관리로 넘어가자) | UnExpectedAccident | CurrentStatusLog | CurrentState
2021-06-01 | 12:00 |  | 14:30 | root lim | ttkmw | workasm gui | 10 min |  | Todo List 정리 및 human resources 서비스 도메인 정의 | 150 min |  |  |  |  | 8 |  |  | 우선순위(가장 긴급)를 작업한 것은 아니지만, 어찌됐든 꼭 필요한 작업들을 했다. 생산성도 좋았던듯? 어쩌면 우선순위에 긴급한 정도 뿐 아니라, 난이도라던지, 병목 유무라던지 등이 같이 고려되는 것도 좋을 것 같다. 어쩌면 workasm gui 가 우선순위가 아니었을지도? |  |  | WorkFinished, TimeTracked,
2021-06-01 | 14:41 |  | 15:06 | root lim | gwldlqslek | 산책 | 5 hour |  | 산책 | 25 min |  |  |  |  | 10 | [5 empty] | WorkFinished, TimeTracked,
2021-06-01 | 15:07 |  | 15:30 | root lim | gwldlqslek | contact@beyondeyesight.group 계정 알아보기 | 50 min |  | beyondeyesight.group 계정 알아보기 | 15 min |  |  |  |  | 10 | [5 empty] | WorkFinished, TimeTracked,
2021-06-02 | 16:00 |  | 16:27 | root lim | gwldlqslek | create intragram accounts | 10 min |  | hawai_heavent_been 계정 만들기 | 10 min + |  |  |  |  | 10 |  |  |  | 1. 2021.6.21 16:26 - 인스타그램 정책 상 하나의 휴대폰으로 여러 계정 생성을 막아놓은 듯. 생성이 안됨. 2. 폰 다른 계정 로그아웃 후 시도중. 3. 아빠 핸드폰으로 해결 |  | Stopped
2021-06-01 | 16:30 |  | 17:30 | root lim | gwldlqslek | 식사 | 2 hour |  | 식사 | 1 hour |  |  |  |  | 10 | [5 empty] | WorkFinished, TimeTracked,
2021-06-01 | 17:30 |  | 18:30 | root lim | gwldlqslek | 이동 |  |  | 이동 | 60 min |  |  |  |  | 5 |  |  | 왜 오래걸렸지? 몰겠음 |  |  | WorkFinished, TimeTracked,
2021-06-01 | 18:30 |  | 20:30 | root lim | gwldlqslek | 산책 |  |  | 산책 및 쇼핑 | 2 hour |  |  |  |  | 8 |  |  | 생각보다 오래 걷긴 했지만 좋았음. |  |  | WorkFinished, TimeTracked,
2021-06-02 | 20:20 |  | 21:26 | root lim | ttkmw | workasm gui | 5 hour |  | workasm gui 중 Or divider | 1 hour |  |  |  |  | 9 |  |  | 일단 작업 자체는 잘했다. 그런데 Expected Work를 너무 크게 잡았다. 상황에 따라 크게 잡을지, 작게 잡을지를 정해야할듯. |  |  | Stopped
2021-06-01 | 21:26 |  | 22:06 | root lim | gwldlqslek | 이동 | 50 min |  | 이동 | 40 min |  |  |  |  | 10 | [5 empty] | WorkFinished, TimeTracked,
2021-06-02 | 22:06 |  |  | root lim | chillVibe | jiyeon said compose | 10 min | [13 empty] | Stopped
2021-06-02 | 12:04 |  | 13:04 | root lim | gwldlqslek | work(task) 관리 | 2 hour |  | work(task) 관리 | 60 min |  |  |  |  | 9 |  |  | 작업 good, expect가 아쉬움. |  |  | WorkFinished, TimeTracked,
2021-06-02 | 13:09 |  | 13:19 | root lim | gwldlqslek | rest - drink and walk | 10 |  | rest -drink and walk | 10 min |  |  |  |  | 10 | [5 empty] | WorkFinished, TimeTracked,
2021-06-02 | 13:20 |  | 15:46 | root lim | gwldlqslek | create instagram accounts | 2 hour |  | create instagram accounts | 2 hour |  |  |  |  | 9 |  |  | 작업 굿, 허나 인스타그램 정책상 다하진 못함. |  |  | Stopped
2021,.6.2 | 15:55 |  | 16:05 | root lim | gwldlqslek | register for changeup | 20 min |  | register for changeup | 10 min |  |  |  |  | 10 | [5 empty] | WorkFinished, TimeTracked,
2021-06-02 | 16:13 |  | 17:30 | root lim | gwldlqslek | eat | 1 hour |  | eat and walk | 1.5 hour |  |  |  |  | 9 |  |  | 굿, estimation 아쉽 |  |  | WorkFinished, TimeTracked,
2021-06-02 | 17:30 |  | 18:37 | walk | gwldlqslek | walk | 30 min |  | walk | 67 min |  |  |  |  | 6 |  |  | estimation 아쉽 |  |  | WorkFinished, TimeTracked,
2021-06-02 | 18:50 |  | 19:20 | root lim | ttkmw | workasm gui 중 Main Section | 2 hour |  | workasm gui 중 design Management Section | 0.5 hour |  |  |  |  | 8 |  |  | 작업 굿, 허나 Expected Work를 너무 크게 잡음. |  |  | WorkFinished, TimeTracked,
2021-06-02 | 19.21 |  | 19:51 | root lim | gwldlqslek | Rest | 20 min |  | Rest | 31 min |  |  |  |  | 8 |  |  | 너무 많이 쉼 |  |  | WorkFinished, TimeTracked,
2021-06-02 | 19:52 |  | 20:15 | root lim | ttkmw | Management Section 중 Layout | 1 hour |  | Management Section Layout에 필요한 Component 리서치 | 25 min |  |  |  |  | 9 |  |  | 작업에 대한 피드백보다… 이게 실제로 뭘 하는가에 대해 정확히 expect 하기가 너무 어려운듯. |  |  | WorkFinished, TimeTracked,
2021-06-02 | 20:16 |  | 20:31 | root lim | ttkmw | rest | 15 min |  | rest | 15 min |  |  |  |  | 10 | [5 empty] | WorkFinished, TimeTracked,
2021-06-02 | 20:32 |  | 21:24 | root lim | ttkmw | Management Section 중 Layout 구현 | 1 hour |  | Tab 구현 일부 | 1 hour |  |  |  |  | 8 |  |  | 힘들어죽겄다 |  |  | Stopped
2021-06-03 | 13:00 |  | 13:40 | root lim | gwldlqslek | rest | 30 min |  | rest | 40 min |  |  |  |  | 9 | [5 empty] | WorkFinished, TimeTracked,
2021-06-03 | 13:40 |  | 13:50 | root lim | gwldlqslek | Not Expected | Not Expected |  | eat | 10 min |  |  |  |  | 8 |  |  | 배고파서 먹었는데, 계획에 없었다는 점에서 2점 감점. 생각보다 내가 빠르게 먹는구나… 아마도 비건그레인 먹어서이미 배불러서그런듯 |  |  | WorkFinished, TimeTracked,
2021-06-03 | 13:50 |  | 14:30 | root lim | gwldlqslek | rest | 20 min |  | rest | 40 min |  |  |  |  | 9 |  |  | 푹 쉼. 내가 생각보다 산책을 엄청 하는구나… 알게됨. |  |  | WorkFinished, TimeTracked,
2021-06-03 | 14:30 |  | 14:48 | root lim | gwldlqslek | make out record time | 5 min |  | make out record time | 18 min |  |  |  |  | 5 |  |  | 아마 커피 기다리고 이런거까지 쳐져서 18분이나 걸린듯 |  |  | WorkFinished, TimeTracked,
2021-06-03 | 14:50 |  | 15:00 | root lim | gwldlqslek | make out todos and dones | 30 min |  | make out dones | 10 min |  |  |  |  | 5 |  |  | 실수로 makeout dones 만 하고 makeout todos를 안했다. 컨텍스트비용을 증가시킴 |  |  | WorkFinished, TimeTracked,
2021-06-03 | 7:00 |  | 11:00 | root lim | gwldlqslek | workout, breakfast, wash | 2 hour |  | workout, breakfast, wash | 4 hour |  |  |  |  | 9 |  |  | 와 기타등등 하는데 4시간 걸리는구나… 생각지 못한 소득 |  |  | WorkFinished, TimeTracked,
2021-06-03 | 11:00 |  | 13:00 | root lim | gwldlqslek | enroll change up program | 10 min |  | enroll change up program and unexpected recording my info, started broadcast | 120 min |  |  |  |  | 10 |  |  | 계획하지 않은 작업을 했지만, 집중해서 처리했음. 게다가 꼭 해야했던 작업을 여기서 운좋게 처리하게됨. |  |  | WorkFinished, TimeTracked,
2021-06-03 | 15:01 |  | 15:20 | root lim | gwldlqslek | rest | 10 min |  | rest | 20 min |  |  |  |  | 8 |  |  | 실환가? 컨텍스트 스위칭에는 진짜 큰 비용이 드는구나 |  |  | WorkFinished, TimeTracked,
2021-06-03 | 15:20 |  | 15:52 | root lim | gwldlqslek | make out todos | 20 min |  | make out todos | 30 min |  |  |  |  | 10 |  |  | 중요한 작업을 함. |  |  | WorkFinished, TimeTracked,
2021-06-03 | 15:52 |  | 16:30 | root lim | gwldlqslek | rest | 20 min |  | rest | 40 min |  |  |  |  | 6 |  |  | 증말 끝도 없이 산책하는구나;; |  |  | WorkFinished, TimeTracked,
2021-06-03 | 16:30 |  | 16:40 | root lim | ttkmw | Management - Self Section | 3 hour |  | Tab Research | 0.15 hour |  |  |  |  | 10 |  |  | 갑작스럽게 멈춤 |  |  | WorkFinished, TimeTracked,
2021-06-03 | 16:40 |  | 17:18 | root lim | ttkmw | 화장실 및 이동 | 40 min |  | 화장실 및 이동 | 30 min |  |  |  |  | 10 | [5 empty] | WorkFinished, TimeTracked,
2021-06-03 | 17:18 | 2021-06-03 | 20:10 | root lim | ttkmw | Management - Self Section | 3 hour |  | Management - Self Section - layout 80% | 3 hour |  |  |  |  | 9 |  |  | 집중력 굿, 작업 속도 굿, estimation bad |  |  | WorkFinished, TimeTracked,
2021-06-03 | 20:10 | 2021-06-03 | 20:23 | root lim | Shawn Killian | 프러덕션 - 체인지업 커뮤니케이션 | 30 min |  | 13 min | [5 empty] | 10 | [5 empty] | WorkFinished, TimeTracked,
2021-06-03 | 20:23 | 2021-06-03 | 22:30 | root lim | gwldlqslek | 이마트 쇼핑 | 2 hour |  | 이마트 쇼핑 | 2 hour |  |  |  |  | 10 | [5 empty] | WorkFinished, TimeTracked,
2021-06-03 | 23:03 | 2021-06-03 | 0:56 | root lim | Shawn Killian | 프러덕션 작업 | 1 hour |  | 2 hour | [5 empty] | 8 | [5 empty] | WorkFinished, TimeTracked,
2021-06-03 | 22:30 | 2021-06-03 | 23:03 | root lim | gwldlqslek | 밥, 물품정리 | 30 min |  | 밥, 물품정리 | 30 min |  |  |  |  | 10 | [5 empty] | WorkFinished, TimeTracked,
2021-06-04 | 0:59 | 2021-06-04 | 5:02 | root lim | gwldlqslek | sleep | 8 hour |  | sleep | 4 hour |  |  |  |  | 1 |  |  | 왜 이렇게 적게 잤지? 너무 신나고 재밌어서인지 자기 전에도 살짝 흥분 상태였음. 그래서인지 해괴한 꿈을 꿈. 당시 너무 무서웠음. |  | Happened: FacedAntAtDream, Happened: IdeaCreated_LyricCameUp(ShameOnYouBlameOnYou) | WorkFinished, TimeTracked,
2021-06-04 | 11:57 | 2021-06-04 | 12:20 | root lim | gwldlqslek | record times at tracker | 20 min |  | make out domain models of workasme and human resources service | 23 min |  |  |  |  | 9 |  |  | 작업 자체는 굿이었지만, expected와 actual work이 아예 다름. 그래서 완전히 점수 깎일 뻔 했는데, 다행히 바로 방향 조정함. |  |  | WorkFinished, TimeTracked,
2021-06-04 | 12:20 | 2021-06-04 | 12:52 | root lim | gwldlqslek | record times at tracker | 20 min | Work | record times at tracker - only Start, End Time And Actual Work | 32 min |  |  |  |  | 3 |  |  | 뭔가 새로운 개념들을 적용하면서 적으니까 어려웠다. |  | Happened: BottleNeckCreated(타임트래커가 너무 커져서 보기가 불편함), Happened: DirectionChanged_한방에정리, InterruptedByCoreProject(체인지업 스터디원 문의) | OnGoing, StopedBecauseOfUnexpectedAccident
2021-06-04 | 5:02 | 2021-06-04 | 7:02 | root lim | gwldlqslek | walk | 1 hour |  | walk
2021-06-04 | 7:02 | 2021-06-04 | 7:32 | root lim | gwldlqslek | eat
2021-06-04 | 7:32 | 2021-06-04 | 9:00 | root lim | gwldlqslek | walk |  |  |  |  | Actual
2021-06-04 | 9:00 | 2021-06-04 | 10:00 | root lim | gwldlqslek | clean up body
2021-06-04 | 10:00 | 2021-06-04 | 11:00 |  |  | walk(Required)
2021-06-04 | 11:00 | 2021-06-04 | 23:57 | root lim | gwldlqslek | talk with Other person
2021-06-04 | 12:57 | 2021-06-04 | 13:35 | root lim | Shawn Killian | respond to customer of beyondeyesight.production | 20 min | Work | respond to customer of beyondeyesight.production, 운영 관련 두가지 사항(마감 댓글, 질문) | 23 min |  | ShawnKillianFocustedOnMainProject(ByUnexpectedAccident), ShawnKillianIFocusedOff(ByBottleNeckHappend) |  | Publish홍보GuideToPublic(BottleNeckSloved) | 10 |  |  |  | Happened: CommunicationNeededWithThirdParty, ThirdPartyHealthCheckFailed | Happened: IdeaCreated(WorkasmeDomainModel_SuccesiveWorkOn) | OnGoing, StoppedByBottleNeck
2021-06-04 | 2:26:00 PM(10분간 Chore발생 - Workasme가 도와줄 수 있는 부분 발견!) | 2021-06-04 | 15:17 | root lim | RootLimSecretary | heal RootLim | 40 min | Work(RootLim 입장에선 Rest) - 여기에서 TimeCreated가 일어나게 할 수도 있을듯?. | heal RootLim +@(removed Required task) | 50 min |  | RootLimSecretaryFocused(BygwldlqslekOnRest) |  | alert Shawn Killan that you should publish the pamplet on 23:59(TriggeredBy TimeCountingToSolveCoreBottleNeckFinished), Make Shawn KillianFocused | 10 |  |  | 반드시 해야하는 Task인 밥먹기를 한번에 없애서, Time Create 성공 | null | null | TimeTracked, WorkComplete
2021-06-04 | 14:26 | 2021-06-04 | 15:17 | root lim | gwldlqslek | rest | 40 min | Rest | rest + @(eat - required) | 50 min |  | gwldlqslekInRestOn(ByShawnKillianIFocusedOff) |  | null | 10 |  |  | RootLimSecretary의 말을 잘 따라서 Time Create 성공 | null | null | TimeTracked, WorkComplete
2021-06-04 | 13:41 | 2021-06-04 | 14:26 | root lim | Shawn Killian | Not Expected | 0 sec | Work(효과성은없지만반드시필요한Work이라는말을 넣을까? | did best to respond to BottleNeck | 45 min |  | ShawnKillianFocusted어쩔수없이 |  |  | 10 | CommunicateWithThirdPary, SetAlarmForShanKillain, TurnOnAriConditionalFofrShawnKillan, AskedFeedBackToVeteran, MakeUpFruitsAndSkinCareForShawnKillain | BuildUpEffectOccured, SolvedCanBeIssueCommunicationTask, InspiredAlgedBoy, LyricIdeaCreated:MyMaTaskBiggerThanUrProject | 불확실한 ThirdParty와의 협업에 잘 대응 | TimeCountingStartedToStartCommandToSolveCoreBottleNeck | ThirdPartyHealthCheckFailed | TimeTracked, WorkComplete
2021-06-04 | NotExpectedSuddenPoint | 2021-06-04 | NotExpectedSuddenPoint | root lim | AlGEDBoy | NotExpected | NotExpected | IdeaCreated | FeedWorkasme | NotExpectedWorkasmePoint |  | FeeldWorkasme, Highlited | BeyodEyesightProductionSecretary:InspiredAlgedBoy | CreateSong, RespectBeyondEyesightProductionSecretary | 11 | null | null | null | null | MacBookKeyboardBroken, FeedWorkasme, ErrorOccured:WhereIsTheSelfFeedbackScore? | FeeledWorkasme, Highlighted | OnSleep
2021-06-04 | 15:38 | 2021-06-04 | 16:28 | root lim | Shawn Killian | create curricularm for MainCoreClient | 1 hour | Work(핵심작업이라는 말도 넣을까?) | Just 실라버스 | 0.8 hour |  | ShawnKillianKnockedDown |  | StartGetRestedCommand | 5 | A |  | 집중력은 괜찮았는데, 아우풋이 별로. | null | null | TaskStopped
2021-06-04 | 16:30 | 2021-06-04 | 22:00 | root lim | RootLimSecretary | heal Shawn Killain | 1 hour | CoreTask | heal Shawn Killain, RecordedTimesForRootLim, DefinedDomainModelsForWorkasmeProject | 5 hour |  | RootLimSecretaryFocused | ShawnKillianKnockedDown | AlsertShanKillianToFocusCommand | 10 |  | Inspired |  |  |  | OnGoing, TaskFinished | TaskFinished
2021-07-01 | 19:12 | 2021-07-01 | 22:30 | root lim | ttkmw | Management - Self Section | 3 hour | CoreTask | Management Self Section 중 layout | 3 hour |  | RootLimSecretaryFocused | ttkmwStopped | RootLim work out | 8 | 뭘 그렇게 많이 쳐먹냐…. | null | 코딩 오랜만에 한거치고 좋았는데, 이것저것 먹은게 너무 많음 | null |  | TaskStopped, TimeTracked | TaskStopped
2021-07-01 | 22:30 | 2021-07-01 | 23:11 | root lim | RootLimSecretary | make root lim work out | 1 hour | CoreTask | make root lim work out | 0.6 hour |  | RootLimSecretaryOff | TaskFinished:RootLimSecretary | junk sound make beat | 10 | 여기다 뭐쓰는거였지? | null | 운동 굿 | null | IdeaCreated:RootLim:비서가 일정조정 및 외부 만남(회의) 등 정리하게하기. 그리고 한 User당 한 Secretary를 둬야 기록하기 편한듯 | TaskStarted, TaskFinished | TaskFinished
2021-07-01 | 23:27 | 2021-07-02 | 0:11 | root lim | junksound | make one beat | 1 hour | CoreTask | make one beat | 0.6 hour |  | JunkSoundFocused | JunkSoundReady? Or RootLimWashFinished | MakeAnotherBeatWithFLStudio(JunkSoundMakingBeatFinished) | 8 |  | null | null | null | null | TaskStarted, TaskFinished, TimeTracked | Timetracked
2021-07-02 | 11:54 | 2021-07-02 | 13:08 | root lim | RootLimSecretary | wash body | 1 hour | Work | wash body | 1 hour | Work | RootLimSecretaryFocused | RootLimWakedUp | TtkmdDoTaskCommand(WashFinished) | 10 |  | null | null | null | null | TaskStarted, TaskFinishehd, TimeTracked | Timetracked
2021-07-02 | 13:08 | 2021-07-02 | 13:30 | root lim | RootLimSecretary | walk | 20 min | 어쩔수없는(이동) + physical | walk + @(과일 먹기) | 20 min | 어쩔수없는(이동) + physical |  |  |  | 10 |  | null | null | null | null | Timetracked | Timetracked
2021-07-02 | 13:30 | 2021-07-02 | 15:42 | root lim | ttkmw | do develop task | 3 hour | Work | do develop task | 2 hour | Work |  |  |  | 10 |  | null | null | null | null | Timetracked | Timetracked
2021-07-02 | 15:42 | 2021-07-02 | 16:30 | root lim | RootLimSecretary | heal RootLim | 1 hour | Work(비서 입장. 물론 너무 많이 쉬게하면 안됨) | rest | 1 hour | Work(비서 입장. 물론 너무 많이 쉬게하면 안됨) |  |  |  | 10 |  | null | null | null | null | Timetracked | Timetracked
2021-07-02 | 16:30 | 2021-07-02 | 17:12 | root lim | ttkmw | do develop task | 2 hour | Work | do develop task | 0.7 hour | Work |  |  | chillvibe:createsong | 10 |  | null | null | null | null | Timetracked | Timetracked
2021-07-02 | 17:12 | 2021-07-02 | 17:24 | root lim | RootLimSecretary | make out times
2021-07-02 | 17:24 | 2021-07-02 | 18:27 | root lim | RootLimSecretary | eat
2021-07-03 | 18:27 | 2021-07-03 | 19:27 | root lim | RootLimSecretary | buy 외장하드
2021-07-03 | 19:24 | 2021-07-03 | 22:25 | root lim | RootLimSecretary | ? | ? | ? | ? | 3 hour | ? | null | null | null | 0 |  | null | 타임트랙 실패 | null | null | TimeTrackFailed | TimeTrackFailed
2021-07-03 | 22:25 | 2021-07-03 | 23:25 | root lim | chillVibe | make beat | 1 hour | Work | make beat | 1 hour | Work | null | null | null | 9 |  | null |  | null |  | TaskStarted, TaskFinished, TimeTracked | TimeTracked
2021-07-03 | 11:00 | 2021-07-03 | 12:00 | root lim | RootLimSecretary | wash body
2021-07-03 | 12:00 | 2021-07-03 | 13:00:00 PM | root lim | RootLimSecretary | eat
2021-07-03 | 13:00 | 2021-07-03 | 13:57 | root lim | ttkmw | design ui | 1 hour | Work | design gui | 1 hour | Work
2021-07-03 | 13:57 | 2021-07-03 | 14:05 | root lim | RootLimSecretary | heal ttkmw
2021-07-03 | 14:05 | 2021-07-03 | 17:42 | root lim | ttkmw | research gui component | 1 hour | Work | develop gui | 3hour |  |  |  |  | 8 |  |  | 잘하긴했는데, 시간 투자 양이 별로. 중간에 넘 많이쉰듯. | Table을 동적으로 만드는것이 어려움. |  | TaskStarted, TaskStopped, TimeTracked | TimeTracked 역시 로그가 중요함. TimeTracked돼밨자 TaskFinished가 중요한 사람한테는 별거아님.
2021-07-03 | 17:42 | 2021-07-03 | 21:01 | root lim | RootLimSecretary | make out fl, battery | 2 hour | Work | make out fl, battery | 3 hour
2021-07-03 | 21:04 | 2021-07-03 | 21:40 | root lim | RootLimSecretary | heal RootLim | 30 min | Rest
2021-07-03 | 21:40 | 2021-07-04 | 2:00 | root lim | chillVibe | make musics | 1 hour | Work | make beat | 4 hour | Work
2021-07-04 | 2:00 | 2021-07-04 | 7:00 | root lim | root lim | sleep | 6 hour | Rest | sleep | 5 hour
2021-07-04 | 7:00 | 2021-07-04 | 9:00 | root lim | root lim | wash, stretch | 1 hour | Rest, Physical | wash, strech | 2 hour | Rest, Physical
2021-07-04 | 9:00 | 2021-07-04 | 13:09 | root lim | ttkmw | impl table | 3 hour | Work | impl table | 4 hour | Work
2021-07-04 | 13:10 | 2021-07-04 | 14;23 | root lim | RootLimSecretary | rest | 1 hour | Rest | Rest, Move | 2 hour
2021-07-04 | 14:23 | 2021-07-04 | 16:00 | root lim | ttkmw | study and impl table | 2 hour
2021-07-04 | 16:00 | 2021-07-04 | 19:00 | root lim | gwldlqslek | eat and drink | 3 hour | Rest | Rest | 3 hour | Rest
2021-07-04 | 19:00 | 2021-07-05 | 2:00 | root lim | RootLimSecretary | sleep | 1 hour | Rest | sleep | 7 hour | Rest
2021-07-05 | 2:00 | 2021-07-05 | 2:00 | root lim | ttkmw | develop table | 3 hour | Work
2021-07-05 | 11:00 | 2021-07-05 | 12:00 | root lim | RootLimSecretary | wash | 1hour | 필수불가결한일(생활에) | wash | 1hour
2021-07-05 | 12:30 | 2021-07-05 | 14:30 | root lim | ttkmw | research useRef | 2.5 hour
2021-07-05 | 14:30 | 2021-07-05 | 15:00 | root lim | RootLimSecretary | eat, stretch | 1 hour | 필수불가결한일(생활에) | eat
2021-07-05 | 15:01 | 2021-07-05 | 19:00 | root lim | ttkmw | develop table | 3 hour |  | develop table | 4 hour
2021-07-05 | 19:00:00 PM | 2021-07-05 | 20:00 | root lim | RootLimSecretary | rest | 1 hour | Rest | rest | 1 hour
2021-07-05 | 20:00 | 2021-07-05 | 21:00 | root lim | ttkmw | 조건부 렌더링 | 1 hour | Work | 조건부 렌더링 | 1hour
2021-07-05 | 21:00 | 2021-07-05 | 22:00 | root lim | RootLimSecretary | 체인지업 오티
2021-07-05 | 22:00 | 2021-07-05 | 22:40:00 AM | root lim | RootLimSecretary | 산책
2021-07-05 | 22:40:00 AM | 2021-07-05 | 23:20:00 AM | root lim | TrapDaddysDaddy | 4! 소스 찾기 | 1 hour | Work | 소스찾기 | 1 hour
2021-07-05 | 11:30 | 2021-07-06 | 10:00 | root lim | RootLimSecretary | sleep | 6 hour | Rest | sleep | 10 hour
2021-07-06 | 10:00 | 2021-07-06 | 11:00 | root lim | RootLimSecretary | 목욕탕 | 1 hour | Rest | 목욕탕 | 1 hour
2021-07-06 | 11:00 | 2021-07-06 | 2:33 | root lim | ttkmw | dev front | 2 hour | Work | dev front | 3 hour

## records (hidden)
UserName | AccountName | Field | Name | Description | Status | Log | Expected(Self) Period | Actual Period | Start Point | Finish Point | Evaluation(At First/At Last) - 첫인상, 끝인상 | Difficult Point | Importance Level of Difficult Point | Feedback(Self) | Feedback(From coworkers) | What I Learned | Reference
geunwon lim | ttkmw | Documentation | 이전 작업 정리 | 기억 나는 부분까지 이전 작업들을 형식에 맞춰 기록. 이전 작업에 대한 피드백 및 성과 관리 프로그램을 위함. | Finished |  | 1시간 | 3시간 |  |  | 이전에 했던 작업들을 회고할 수 있어서, 이 작업을 하는 것 자체로 스스로 피드백하게 됐다. 이 점에서 좋았다. |  | 상 | 작업을 할 때 풀 리퀘스트 단위로 하다보니, 회고가 쉬웠다.
geunwon lim | ttkmw | Development | 머티리얼 디자인 라이브러리 적용 | react-native-paper 적용 | Finished |  | 1일 | 2주 | 2021-03-21 | 2021-04-29 | 이제껏 객체 지향을 공부했지만, 마땅히 적용할 곳을 찾지 못했다. 그런데 이 작업에서 공부했던 걸 적용해볼 수 있어서 재밌었다. | 플랫폼, 기기들이 달라지는 상황들을 고려하는 것이 어려웠다. |  | 작업 정의가 아쉽다. 처음에 머티리얼 디자인 적용을 하려고 했던 것과 달리, 기기 변경에 유연한 UI 적용까지 해버렸다. 계획은 작게 했으나, 실제 작업을 너무 크게 해버렸다. 그래서 기존 계획보다 기간이 지나치게 많이 소요됐다. |  |  | https://github.com/beyond-eyesight/hy-international/pull/80
geunwon lim | ttkmw | Development | Oauth2 인가 구현 | spring boot 프로젝트에 keycloack 연동 - DB 통일 | Finished |  | 1 Week | 1달 |  |  | 꿀잼 오브 꿀잼. 됐을 때 뿌듯했다. | 디버깅 하는 것이 어려웠다. | 중 | 끈기 있게 한 점이 좋았고, 동시에 효과성이 그다지 없는 작업에 시간을 과하게 썼다. |  | 디버깅 스킬이 많이 는 것 같다. | https://github.com/beyond-eyesight/bintegration/pull/90
geunwon lim | ttkmw | Development | 로컬 서버와 aws cassandra 연동 | 기존에 로컬 서버와 로컬 cassandra가 연동되어 있던 것에서, 로컬 서버와 aws cassandra 연동으로 바꿈 | Finished |  | 1 Day | 3일 |  |  | 공부하는 게 많아서 좋았다. 그다지 어렵진 않았지만 꼭 필요한 부분들이었다. | https 통신 학습 | 상 | 공부를 열심히 한 것이 좋았다. 다만, 알고 보면 쉬운 부분을 빙빙 돌았던 것이 아쉽다. 그래도 이건 공부하기 전에는 어느정도의 기간이 걸릴지 예상하기 어려웠기에 기간 산정에 대해 문제는 없었다고 생각한다. |  | 테스트를 어디까지 할 것에 대한 고민을 했고, 이전보다는 조금 더 명확해진 느낌이다. CassandraConfig를 AutoConfigure 하면서, 기존 테스트가 의미가 없어진 느낌이었다. 기존 테스트가 통과한다고 해서 aws cassandra와 연동되는 것은 아니었기 때문이다. 그래서 TestConfig도 AutoConfigure 할 지 고민했는데, 결국 그러지 않았다. 기존 테스트의 목적이 "연동이 되는가"가 아니라, "이러이러하게 하면 Cassandra와 연결 됨" 정도를 확인하는 것이라고 생각하면, 기존 테스트도 가치가 있다. 중요한 것은 AutoConfigure 테스트가 큰 의미가 없고, 우선순위에서 밀린다는 것이다. 이러한 생각들은 나보다 경력이 많은 개발자에게 자문을 구했다. | https://github.com/beyond-eyesight/bintegration/pull/19
geunwon lim | ttkmw | Development | redis pub/sub | redis template을 활용한 pubsub 구현 및 integration 테스트 | Finished |  | 1 Day | 2주 |  |  | pubsub이 익숙치 않았는데, 해봐서 재밌었다. |  | 하 | 해야할 것들에 비해 시간이 너무 오래 걸렸다. 당시 컨디션이 좋지 않았지만, 그걸 감안해도 오래걸렸다. 개인적으로 원인을 생각해보면, 실력도 부족했고 너무 완벽하려고 했던 것 같다. 현재 생각해봤을 때 굳이 RedisTemplateTest를 작성하지 않아도 됐을 것 같다. |  | 이 작업을 하면서 학습 테스트의 강점을 충분히 느낄 수 있었다. 스프링 개발자들이 만들어놓은 학습 테스트 덕에 내 학습 테스트 작성이 수월했다. | https://github.com/beyond-eyesight/fellowship/pull/24
geunwon lim | ttkmw | Development | 로컬 서버와 로컬 cassandra 연동 | spring data cassandra를 활용해 로컬에서 cassandra 연동 | Finished |  | 4 Day | 22일 |  |  | 재밌긴 했는데 어려웠다. | cassandra 학습 | 중 | 실력에 비해 자신감이 과했다. 이 때 생각해보면, 고급 기술을 써본 경험이 많이 없었는데도 불구하고 금방 할 수 있을줄 알았다. 그래도 분산 db를 써보는 것은 좋은 경험이었다. |  | 내 실력이 한참 부족하다는 것을 배웠다. | https://github.com/beyond-eyesight/fellowship/pull/56
geunwon lim | ttkmw | Development | 채팅 인터페이스 구현 | ChatController를 구현하여, 브라우저와 통신 | Finished |  | 1 Day | 18일 |  |  | 재밌었고 디버깅하면서 실력이 느는 걸 느꼈다. | 파서 디버깅 | 하 | 지금 생각해보면 중요하지 않은 부분인데, 과하게 집착했다. |  | web socket, stomp 통신, 파싱 등에 대해 공부했다. | https://github.com/beyond-eyesight/fellowship/pull/67
geunwon lim | ttkmw | Development | dockerfile의 위치 원하는대로 조정 | gradle-docker-plugin 활용하기 | Finished |  | 2 Hour | 1일 |  |  | gradle 관련 다루는 건 생소했어서 재밌었다. |  |  | 우선순위를 고려하면, 이건 나중으로 미뤘어야 했다. |  | gradle 관련 | https://github.com/beyond-eyesight/fellowship/pull/83
geunwon lim | ttkmw | Development | github action을 활용한 CI/CD | github action을 활용한 빌드, 테스트, 배포, 태깅, 릴리즈 | Finished |  | 1 Week | 10일 | 2020-11-16 | 2020-11-23 | 계속 해보고 싶었던것거라 재밌었다. |  |  | - |  | CI/CD
geunwon lim | ttkmw | Development | 리액트 네이티브를 활용한 UI 작업 | ui 작업 | Failed |  | 1주일 | 18일 | 2021-04-09 | 2021-04-27 | 디자이너와 함께 작업하는 것은 처음이었기에 신기했다. | 일단 인수 조건을 충족시키는 게 최우선인데, 그걸 위해 알면서도 코드 품질을 포기하는 것이 어려웠다. |  | 우선 순위를 먼저 해내는 것이 부족하다. 다른 사람과 협업할 때, 하기로 한 것과 하지 않기로 한 것을 확실히 커뮤니케이션하자. |  | 협업할 때 기간과 관련해서는 정말 확실하게 커뮤니케이션해야 한다는 것을 배웠다.
geunwon lim | ttkmw | Development | 리액트를 활용한 UI 및 배포 | ui 작업 | StoppedTemporarily | 1. 이미지 컨트롤 완료 2. top navigation 완료 - 5.29 17시 34분 3. GetStartedSection 시작 5.30 09:26 4. GetStartedSection 완료 5.30 11:35 - 딱히 한 건 없는거같은데 왜 이렇게 오래거린건지 잘 모르겠다. 5. Sign 페이지 시작 5.30 14:44 6. SignUpSection 중 FullName BelongsTo, ContinueWithGoogle 시작 - 5.31 17:41 7. SingUpSection 마치고 쉬는시간 시작 - 5.31 18:56 8. 외국인 친구에게 용어 피드백 받음(blongs to -> where are you in?) 9. 다시 쉬는시간 시작 10. 6.1 20:40 Management Section에서 Self/Team은 Tab으로 하는 것도 좋을듯 | 3일 |  | 2021-05-25 |  | 시작 전: 기존에 몇번 해본 작업이기에 빠르게 할 수 있어야 한다고 생각했다. |  |  | 1. 중간에 디테일을 좀 더 신경쓰고 싶은 부분이 있었는데, 그 부분을 지나치고 우선순위에 집중한 점 굿. 버튼 클릭했을때 글씨 오렌지색으로 보이면 좋을거같았는데 일단 넘김. 2. 우선순위에 집중 - Button을 Component로 뺄 때, 좀 더 잘 하고 싶긴 했는데 일단 되게 함. 3. 우선순위에 집중하지 못함 - 중요하지도 않은 Floating Label에 30분정도를 날림. 이걸 잘못했다고 하기엔 애매한듯.
geunwon lim | gwldlqslek | Project Management | 여러 사용자의 홍보용 sns 계정 만들기 | 문서 | Finished |  | 1 Day | 1시간 | 2021.5.29 17시 44분 | 2021.5.29 18시 41분 | 시작 전: 디자인 툴을 활용하면 금방 끝낼듯 |  |  | 잘했음 |  |  | 1. https://www.instagram.com/chill_vibe_____/ 2. https://www.instagram.com/junk_sound/
geunwon lim | chillVibe | 작곡 | chill at the and 작곡 마무리 | 제곧내 | 일시정지 | 1. 드럼 작업 중, 룹을 사용하니 원하는대로 되지 않은 상태에서 끝남. | 2일 |  | 시작: 5.30 |  | 운이 좋았음. | 드럼 뤂 커스터마이징
geunwon lim | chillVibe | 작곡 | poll sorang 마무리 | 제곧내 | 완수 | 1. 변주 등 필요 | 1일 | 1시간 | 2021-06-30 11:00 | 2021-06-30 12:00 | 쉽다 |  |  | 이렇게 빨라도 됩니까? |  |  | https://www.instagram.com/p/CPipPoNnshy/
geunwon lim | junksound | 작곡 | before sleep 마무리 | 제곧내 | 완수 |  | 2시간 | 2시간 |  |  | 진짜 빠르게 할 수있을 거 같다. |  |  | 실제로 빨리 끝냈다. 칭찬하고 싶은 부분은 목표 수행 기간과 실제 수행 기간이 일치한다는 점.

## users
Name(Id) | UserNickname(유저에게 보이는, 불리는 이름
??? | root lim

## accounts
Name(추후 UUID 형식으로 변경 필요) | CharacterName | UserName(추후 UserName으로 변경 필요) | HighLevelJob | Job | JobDescription | WhatDoYouDo | WhatDoYouDoDetail | BelongsTo | 열13 | 열14 | 열15
1 | gwldlqslek | root lim
2 | hawai_heaven_tbeen_ | root lim | Artist | Musician
3 | TrapDaddysDaddy | root lim | Artist | Musician
4 | callmegray_______ | root lim | Artist | Musician
5 | AlGEDBoy | root lim | Artist | Musician
6 | K-GAYO | root lim | Artist | Musician
7 | AndreLim | root lim | Artist | Musician
8 | JazzyFault | root lim | Artist | Musician
9 | SouthSouthKorean | root lim | Artist | Musician
10 | uuunoieee | root lim | Artist | Musician
11 | RootLimSecretary(RootLim -> UUID_UserName) | root lim | Supporter | Secretary